## Sheet1
Task Name | Duration | Start | End | 2020-09-21 | [6 empty] | 2020-09-28 | [6 empty] | 2020-10-05 | [6 empty] | 2020-10-12 | [6 empty] | 2020-10-19 | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30
|  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Team Sprint #2_Topic | 7 days | 2020-09-16 | 2020-09-23
Project planning
Project Plan Presentation
Team Sprint #3_Technical | 11 days | 2020-09-23 | 2020-10-04
Define Requirments
Investigation and Analysis
System architectures design
Scipting language clearifation
System prototype planing
System deployment planing
Team Sprint #4_Dev Update | 14 days | 2020-10-05 | 2020-10-18
User interface Design
Database Schema Design
UML diagram plan
Team Sprint #5_Dev Update | 14 days | 2020-10-19 | 2020-11-01
System Setup
System Developing
Initial application deployment
Mid-term Feedback From TA
Team Sprint #6_Dev Update | 14 days | 2020-11-02 | 2020-11-15
System Developing
Flask Implement
API implement
Programming
Team Sprint #7_Deployment | 14 days | 2020-11-16 | 2020-11-29
System Testing
QA and Final TA Review
Final Documentation
System Launch
System Demo Deployment
Team Sprint #8_Presentation | 3 days | 2020-11-30 | 2020-12-02
Project Presentation
Documentation
Finish
Start
Finish
Start
Finished
Start
Finished